## LOU
Sinai Implementation |  |  |  |  | Weeks
[5 empty] | 2016-04-11 | 2016-04-18 | 2016-04-25 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27 | 2016-07-05
Project Organization
Letter of Understanding
1 | Vision
| 1.1 | Patient-centered transportation
| 1.2 | Patient ride experience and health outcomes
| 1.3 | Department staff scheduling experience
| 1.4 | Partner in continuous quality improvement ¦ strengthening competitive advantage
2 | Benefits
| 2.1 | Increased hospital revenue
|  | 2.1.1 | Increase in number of appointments and procedures as a result of reduction in missed appointments
| 2.2 | Improved efficiency
|  | 2.2.1 | Reduction in redundant effort and rework related to rescheduling patients
| 2.3 | Improved patient experience
|  | 2.3.1 | Increase in percent of patients who keep appointments
|  | 2.3.2 | Increase in patient satisfaction with ride experience
| 2.4 | Improved patient outcomes and reduced unnecessary avoidable costs
|  | 2.4.1 | Improved health outcomes
|  | 2.4.2 | Reduced ED use for patient participant ants
Project Organization
Letter of Understanding
3 | Roll-out strategy
| 3.1 | Discovery
|  | 3.1.1 | Overview
|  |  | 3.1.1.1 | Organization structure
|  |  | 3.1.1.2 | Hospital utilization
|  |  | 3.1.1.3 | Hospital revenues and payor mix
|  |  | 3.1.1.4 | Current activity and outcome measures
|  |  | 3.1.1.5 | Current transporation services
|  | 3.1.2 | High-level interviews
3.1.2
| 3.2 | Implementation Modules
|  | 3.2.1 | Module I: Discharge to home
|  | 3.2.2 | Module II: Discharge to home with return follow-up visit scheduled
|  | 3.2.3 | Module III: Series of visits scheduled
|  | 3.2.4 | Module IV: Roll out to remaining departments
| 3.3 | Department level process analysis and planning
|  | 3.3.1 | Department services, organization structure, activity (visits/ procedures) and revenue
|  | 3.3.2 | Current appointment scheduling process analysis
|  |  | 3.3.2 .1 | Observation and analysis of process
|  |  | 3.3.2.2 | Interviews regarding number of missed appointments and impact on operations
|  | 3.3.3 | Revise process
| 3.4 | Training and Support
|  | 3.4.1 | Training
|  |  | 3.4.1.1 | Implementation
|  |  | 3.4.1.2 | On-going
|  | 3.4.2 | Support
|  |  | 3.4.2.1 | Implementation
|  |  | 3.4.2.2 | On-going
4 | Project Team Roles and Responsibilities
| 4.1 | Project decision making structure
|  | 4.1.1 | Sponsor - focused on ensuring project achieves results
|  |  | 4.1.1.1 | Champions project
- articulates vision
- aligns vision with Sinai's overall strategy
- understands stakeholders' needs and gains commitment
Accountable for delivery of planned benefits
Establishes scope and roll-out
Secures funding
Keeps project on track
Removes obstacles
- Escales issues to the right decision maker
Manages politics
|  | 4.1.2 | Project manager
|  |  | 4.1.2.1 | Manages project progress on day-to-day basis (deliverables, timelines, risks and issues)
Manages internal team
Record and manage project issues and escalates as needed
Manages training
Final approval of design specifications
Works with users to ensure project meets their needs
Manages user acceptance testing
Identifies users' training needs
|  | 4.1.2 | Stakeholders
Have interest in, role in or are impacted by the project
Raise awareness at the senior level
Resolving strategic and policy issues
|  | 4.1.3 | Department level users
| 4.2 | Sinai responsibilities
|  | 4.2.1 | Planning data collection
|  | 4.2.2 | On-going data collection and reporting
|  | 4.2.3 | Review and approval
| 4.3 | Kaizen Team
|  | 4.3.1 | Kaizen team organization chart
|  | 4.3.2 | Department set-up and training
|  | 4.3.3 | Technical Assistance
|  | 4.3.4 | Data reporting
|  | 4.3. | Post implementation technical assistance and reporting
Project Organization
Letter of Understanding
5 | Communications
| 5.1 | Project Monitoring
|  | 5.1.1 | Project activity / progress dash board
|  | 5.1.2 | Regularly scheduled progress meetings
| 5.2 | Project roll-out to develop staff and patient engagement
|  | 5.2.1 | Implementation
Communicates goasl to organization as a whole
|  | 5.2.2 | On-going
To staff
To patients and family
6 | Timing and Deliverables
| 6.1 | Major deliverables
|  | 6.1.1 | Contract
|  | 6.1.2 | Pilot platform
|  |  | 6.1.2.1 | Module I
|  |  | 6.1.2.2 | Module II
|  |  | 6.1.2.3 | Module III
|  |  | 6.1.2.4 | Module IV
|  | 6.1.3 | Data collection tools and interview guides
|  | 6.1.4 | Project schedule
|  | 6.1.5 | Dash board
| 6.2 | Timeline
|  | 6.2.1 | Timeline with major deliverables and 3 site roll-out ( Sinai, Schwab, HC)
7 | Fees
| 7.1 | Implementation set-up
| 7.2 | Ride fare escrow account
| 7.2 | Licensing
| 7.3 | Payment terms and schedule

## Interview Questions
General Interview Questions/ topics
1 | Fit with Sinai's current goals and strategies
2 | Related / complementary initiatives
Who should be involved at top level
Types of users who should be involved at the department level
How are successful system implementations handled at Sinai
What are lessons learned from implementations that have not gone well
Impact of poor transportation
on patient
on department
on hospital
Percent of missed appointments
Reason for missed appointments
Scope of current transportation program
Annual budget
Sources of funding
Organizational structure of department
Type and number of inhouse vehicles
Out-sources rides or assistance (services used)
How are rides arranged/ ordered by hospital staff
Types of assistance
- Regular vans
- Wheel chair accessible
Schedules and routes